## Sheet1
Goal: Improve automated test maintenance time
| Maintenance | Execution Time can be optimized , need to check the implementation for waitForReady Method. Test Script Updates .
Flaky areas
Goal: Improve Automated test analysis time
Framework Improvement
1 | Parallel execution | Dockerization, Multiple Agents Configuration - Framework Changes Required.
| Log improvement | To be Analysed
Pipeline Management
Environment selection
Module base execution
2 | Goal: Improve the test data creation process
Automate test data creation for existing scripts- M5
Automate test data creation for existing scripts- FA
PreSetUp Data Approach to be re-visited .Should continue with current Approach or Data Injection by SQL/Oracle Script ?
Screenshots Capturing
ExtentReport Enhacements
Automated Report through e-Mail post Test Suite Completion
TestRail Integration
Internal Review Process to be Refined.
WebElement unique ID's to be provided while Page Development.
Stabilization of Test on Other Test Environment.

## Task_list_FY2023
Priority | Tasks | AssetWorks | R-Systems | Efforts | Dependencies | Risk | Queries/ Remarks
1 | Data Restore through Automation for SQL Env. | AW DBA will provide SQL queries to inject environment databases from baseline DB. As discussed with Musarrat, For Oracle Env. Data Restoration will not be applicable, AW will be taking ownership for restoration manually. | Framework Support to restore the db backup in respective environment through Automation Test Suite Run. Queries Updates might be required on Application Version Update. | 60 Hrs. - M5 | 1.) AW to provide backup scripts at a physical location that need to be restored through automation scripts. 2.) Data to be created as part of baseline database need to be provided by AW. | Currently, No clearity for FA. How data restoration will work and what will be its benefits??? If it will be as same as M5 then effort will be same. | Can we add Pre-SetUp Data also through queries.
| Alternative to above approach : Batch File can be run and confiured as Azure Stage. | Stage to be created in Azure Pipeline. | Creation of Batch File. | 40 Hrs-M5
2 | Parallel Execution- Module Based | Multiple Agent Configuration on Azure | Multiple Agent-Framework Changes to support Parallel execution for Module Based approach. | 90-Hrs | AW side to provide multiple agents. AW to set up Multiple Agent on Pipeline .
3 | Goal: Improve the test data creation process Automate test data creation for existing scripts- M5 Automate test data creation for existing scripts- FA | 1. To Provide Queries for New Pre-Set Up Script Creation and Steps if New Create Method needs to be developed. | 1. New PreData SetUp Scripts Creation. 2. New Create methods for Handling Pre-Data Creation. 3.Adding New Data To Existing Pre-SetUp Scripts. 4. Any Environmental related Data or UI gaps Handling. | 60-Hrs -M5 |  | Currently, No clearity for FA side, Analysis would be required. If pre- set up creation required for existing testcases, that wolud required extent amount of efforts. | M5 - 462 test cases FA - 457 till sprint 11
4 | Current Suite Maintenance |  | 1. Execution Time Optimization. 2. Data Cleanup per Test Script- Delete Methods whereever possible. 3. Flaky Tests to be stabilized. 4. Logout the Application after each test Run. 5. Code refactoring for existing Generic Methods/ for some testcase scripts. 7. For other child Tests cases , exclude launching the browser to minimize execution time. 8.Object Model Conversion. | 120- Hrs
5 | Screenshots Capturing |  | OK
6 | TestRail Integration |  | OK
7 | Hierachical Log Display | Need more discussion with Musarrat for requirement Understanding | Need to Analysed at R-sys

## EffortsEsitmation_M5_FA
Priority | Epic | Stories | Efforts | Ownership | Product | Risks | Querries
| Data Restore through Automation for SQL Env. | 1. Automation Framework changes to Support data restoration of baseline db. | 30 | R-Systems | M5 | Currently, No clearity for FA. How data restoration will work and what will be its benefits??? If it will be as same as M5 then effort will be same. | Can we add Pre-SetUp Data also through queries.
|  | 2. Queries Updates might be required on Application Version Update. | 10 | R-Systems
|  | 3. AW DBA will provide SQL queries to inject environment databases from baseline DB. |  | AW
|  | 4. Conversion of backup file to selenium C# supported format with Logging and assertion implememtion will be required for sequencial query execution. (As discussed with Musarrat) | 50 | R-Systems
|  | 5. Maintenance required | 20
|  | 6. Testing- Comaptibility check with existing test suite/ framework. | 20 | R-Systems
| Alternative to above approach : Batch File can be run and confiured as Azure Stage. | 1. Converting SQL File shared by DBA to executable Batch File. |  | AW | Both |  | Restoration of baseline db will done by batch file whenever needed, and will be owned by AW
|  | 2.Testing of created Executable File. |  | AW
|  | 3.Execution of Batch File from Azure Stage. |  | AW
|  | 4. Maintenance of Batch File - Ongoing Process |  | AW
| Parallel Execution- Module Based | 1. Multiple Agent Configuration on Azure. |  | AW | Both
|  | 2.Multiple Agent-Framework Changes to support Parallel execution . | 60 | R-Systems
|  | 3.Framework Support to Run Tests Module wise. | 40 | R-Systems
|  | 4. Testing | 30 | R-Systems
|  | 5. Updating Test Category For Existing Tests. | 20 | R-Systems |  |  | FA- 35 files, M5- 40
| Goal: Improve the test data creation process Automate test data creation for existing scripts- M5 Automate test data creation for existing scripts- FA | 1. AW to provide queries for remaining Pre-Set Up required for existings Scripts. |  | AW | Both | Currently, No clearity for FA side, Analysis would be required. If pre- set up creation required for existing testcases, efforts may vary. | M5 - 462 test cases
|  | 1. Pre setup data creation for FA existing testcases (efforts includes after testing as well) | 160 | R-Systems |  |  |  | Currently, ~37 creation methods in FA
|  | 1. Pre- SetUp Data Scripts Creation for Existing Tests (For which Create Methods Exists) | 30 | R-Systems |  |  | FA - 457 till sprint 11
|  | 2.Adding New Data To Existing Pre-SetUp Scripts. | 30 | R-Systems
|  | 3. Any Environmental related Data or UI gaps Handling. | 20 | R-Systems
|  | 2. New Create methods for Handling Pre-Data Creation -New Creation Method Script Should be counted as Functional tests. |  | R-Systems
| Current Suite Maintenance | 1. Execution Time Optimization. | 40 | R-Systems | Both
|  | 2. Data Cleanup per Test Script- Delete Methods whereever possible. | 40 | R-Systems
|  | 3. Pipeline Flaky Tests to be stabilized. | 80 | R-Systems
|  | 4. Logout the Application after each test Run. | 10 | R-Systems
|  | 5. Code refactoring for existing Generic Methods/ for some testcase scripts. | 50 | R-Systems
|  | 7. For other child Tests cases , exclude launching the browser to minimize execution time. | 20 | R-Systems
|  | 8. Object Model Conversion. | 40 | R-Systems
| Screenshots Capturing | Screenshots for failed cases implementation | 20 | R-Systems | Both | Not sure about finalization of tool.
|  | Screenshot integration with testrail | 40 | R-Systems
|  | Research required to find best suitable tool to capture the screeshot. | 20 | R-Systems
| TestRail Integration | Need to analysis for module wise execution/ parallel execution | 60 | R-Systems | FA | Estimates provide based on FA, If require same for M5, more efforts will be required.
|  | Need to update testcase ids to sync with testrail ids | 50
|  | Need to analysis how to create testrun in testrail with desired testcases | 20

## Estimates_2023
SprintWise Per Head Resource on M5 Automation
Total Test Case Count (Post Refinement) | Tasks Per sprint | Efforts (Hrs) Per Tasks | Efforts (Hrs) Per Script
Medium | 4 | 8 | 32
High | 4 | 10 | 40
Very High | 1 | 18 | 18
Test Automation Efforts for M5 | 9 |  | 90
SprintWise Per Head Resource on FA Automation
Total Test Case Count (Post Refinement) | Tasks Per sprint | Efforts (Hrs) Per Tasks | Efforts (Hrs) Per Script
Low | 4 | 3 | 12
Medium | 4 | 6 | 24
High | 3 | 10 | 30
Very High | 2 | 12 | 24
Test Automation Efforts for FA | 13 |  | 90
Productive Hrs: 90 Per Head per sprint |  |  | Per Test Script Tasks
Sprint refinemnet and grooming should happen in advance. |  |  | Test case grooming
Create, Update and Delete Tests should be included in same Sprint |  |  | Automation scripting
Multiple tabs functinality should be divided into different Tests cases (No merging of tab wise features). |  |  | JSON Data and presetup data creation
Module should be stable and bug free. |  |  | Review
Validation and acceptance criteria should be well defined. |  |  | Merge to develop and Azure Pipeline Fixes for Test